**Commercial Terms : Fasteners**

         Price  : For Site basis

         Taxes  : As applicable, GST @ 18% in prevailing tax regime

         Freight  : Inclusive

         Insurance : Inclusive

         Warranty : 10 Years from the date of supply.

         Payment Terms  : 90% within 45 days against material delivery at site, balance 10% against submission of PBG of equivalent value or after 1 year of the supply. Vendor to share GST payment proof in order to claim GST amount from ReNew as a part of their payment.

         CPBG : Contract Performance Bank Guarantee to be issued for entire contract period for 10% of the basic contract value within 7-10 of the contract signing.

* Liquidate Damage :   LD will be applicable for any delay in delivery beyond completion date @ 1% of the contract value per week basis for the maximum of 10% of the total contract value.
* Delivery Schedule :

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
| 110MW Solar PV Plant - Rajasthan | | | | |
| **Project** | **HDG** | **From** | **To** | **Quantity ( %)** |
| 110 MW | 1st Lot | 01-05-20 | 10-05-20 | 50% |
| 2nd Lot | 11-05-20 | 20-05-20 | 30% |
| 3rd Lot | 21-05-20 | 30-05-20 | 20% |

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
| 105MW Solar PV Plant -  Gujarat | | | | |
| **Project** | **HDG** | **From** | **To** | **Quantity ( %)** |
| 105 MW | 1st Lot | 01-05-20 | 10-05-20 | 50% |
| 2nd Lot | 11-05-20 | 20-05-20 | 30% |
| 3rd Lot | 21-05-20 | 30-05-20 | 20% |

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
| 300MW Solar PV Plant - SECI III | | | | |
| **Project** | **HDG** | **From** | **To** | **Quantity ( %)** |
| 300 MW | 1st Lot | 01-05-20 | 20-05-20 | 50% |
| 2nd Lot | 21-05-20 | 10-06-20 | 30% |
| 3rd Lot | 11-06-20 | 30-06-20 | 20% |