## Sheet1
Sr.No. | Item | Remarks | Effort
1 | Chat Functionality | Need to understand the current implementation . Based on that we should be able to finalize whether we will be using the same implementation or we can go for Quickblox kind of third party api(quickblox.com) which provides more features and better User experience. Here for each trip there will be a group created where all the participent will be by default joined in the group. Using system like quickbox we would be able to scale it to the Mobile platform also in future. Also user can send attachments like pictures. | 3-4 weeks
2 | Inbox | This can be merged with Chat system. Need to be discussed.
3 | Bugs while sending email communication at various stage of customer interaction | Need more details on this.
4 | Signup | Need to discuss the current fields . We whould be showing only 3-4 fields only which is highly required and rest can be skipped for lateral entry. | 2-3 Days
5 | Google Analytics |  | 1 Day
6 | Install cookies to track & monitor login history & location of customers |  | 1 Day
7 | UI/UX |  | 2-3 weeks
8 | Time Slot for Create Plan ?? | What is the relevance ?