## Sheet1
S. No | Nature | Priority | Issue | Action By | Status | Check by AA
1 | Operational | 1 | Remove Event Time Alteration (Duplication) – To be removed from Menu Item | Sunil | Done | Done
2 | Operational | 1 | www. vs https://procurengine.com log in | Sunil | Done | Done
3 | Operational | 1 | Sequence of items gets mixed up and time is not getting updated properly in staggered items |  |  | Done
4 | Operational | 1 | Staggering Bids – Time / date change needs correlation with bid items |  |  | Done
5 | Operational | 1 | Graphs |  |  | Done
6 | Operational | 1 | Staggered Bids – Time Duration is not getting extended for the complete bid in case individual bid time is increased using time alteration |  |  | Done
7 | Operational | 2 | Individual bid Closing time in Staggered Bid - minute in single digit, i.e 16.01 is shown as 16.1
8 | Operational | 2 | No of Decimals in Bid Summary sometimes is not complete, i.e. 868,729.3600000001 comes in place of 868,729.36 etc
9 | Operational | 5 | Closing time for individual items in bid summary to the admin (For Staggering Items)
10 | Operational | 2 | Auto log-out issue in RA
11 | Operational | 2 | Auto Email to vendors in case of Date/Time is Altered
12 | Operational | 2 | RFQ Vendor selection must be in similar to vendor invide of reverse auction
13 | New | 3 | Create RFI
14 | New | 3 | Status of Open RFI/RFQ/VQs
15 | New | 3 | Re-open / extension of RFQ/RFI
16 | New | 3 | Revert Option (Approve/Reject/Revert) in RFI/RFQ/VQ
17 | New | 3 | RFI – RFQ – RA Item Fetch
18 | New | 3 | RA Excel upload (Similar to RFQ)
19 | Operational | 2 | L0 issue
20 | Operational | 2 | Last 5 seconds bid extension
21 | Operational | 4 | Dutch auction same price validation
22 | Operational | 5 | Provision to show L1 / H1 price to Bidders who are not L1/H1
23 | Operational | 5 | Provision to enter Initial Vendor Prices by the administrator and display to vendor before the bidding

## Sheet2
Bid Id, Item ID
| Bid Entry Time | Value | Vendor